## Product Backlog
MoSCoW ID | Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | Complexity | Risk/ Impact(L-Low, M- Medium, H-High) | Type | Comments
1 | 1 |  | M | Us:101 | Participant must create his Account (enrollParticipant()) | Simple | L | Functional
2 | 2 |  | M | Us:102 | Participant must login into the module | Complex | H | Functional
3 | 3 |  | S | Us:103 | Participant can check for available courses | Very Simple | L | Functional
4 | 4 |  | S | Us:104 | Participant can check for available training programs | Very Simple | L | Functional
5 | 5 |  | C | Us:105 | Participant can choice a training program (Id genrated automatically) | Very Simple | L | Functional
6 | 6 |  | C | Us:106 | Participant can view the training opt for | Very Simple | L | Functional
7 | 7 |  | C | Us:107 | Participant can cancel or modify a training opted | Very Simple | L | Functional
8 | 8 |  | M | Us:108 | Participant should have 12-digit Unique Identification number | Average | L | Functional
9 | 9 |  | C | Us:109 | Participant can change their credentials | Average | M | Functional
10 | 10 |  | M | Us: 110 | Participant can add feedback | Simple | H | Functional
11 | 11 |  | C | Us: 111 | Participant can update feedback | Average | L | Functional
12 | 12 |  | C | Us: 112 | Participant can delete account | Simple | L | Functional
13 | 13 |  | M | Us: 113 | Admin can login into the application | Complex | H | Functional
14 | 14 |  | M | Us: 114 | Admin can add courses, add trainers | Simple | L | Functional
15 | 15 |  | M | Us: 115 | Admin can view feedback reports, view feedback defaulters report | Very Simple | L | Functional
16 | 16 |  | C | Us: 116 | Admin can view , cancel or modify courses | Average | L | Functional
17 | 17 |  | C | Us: 117 | Admin can delete or modify Trainers | Average | L | Functional
18 | 18 |  | C | Us: 118 | Admin can view participants | Very Simple | L | Functional
19 | 19 |  | C | Us: 119 | Admin can view Trainers (viewAllTrainers) , can view Skill set wise trainers (viewAllaTrainers(skills)) | Very Simple | L | Functional
20 | 20 |  | M | Us: 120 | Co-ordinator can login into the application | Complex | H | Functional
21 | 21 |  | M | Us: 121 | Co-ordinator can add training programs | Simple | L | Functional
22 | 22 |  | C | Us: 122 | Co-ordinator can view training programs | Very Simple | L | Functional
23 | 23 |  | C | Us: 123 | Co-ordinator can update training programs | Average | L | Functional
24 | 24 |  | C | Us: 124 | Co-ordinator can remove training programs | Simple | L | Functional
25 | 25 |  | C | Us: 125 | Co-ordinator can view participants | Simple | L | Functional
26 | 26 |  | M | Us: 126 | Co-ordinator can view feedback reports, view feedback defaulters report | Simple | L | Functional
27 | 27 |  | M | Us: 127 | Authentication of the User(Valid/Invalid User) | Average | M | Functional
28 | 28 |  | S | Us: 128 | Session Timeout(if no activity) | Very Simple | M | Functional
29 | 29 |  | S | Us: 129 | Participant can Logout | Very Simple | L | Functional
30 | 30 |  | M | Us: 130 | Asking for choice again on wrong selection | Average | L | Functional

## Sprint Backlog
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment
P:01 | Us:113 | 1 | POJO class for Admin | Joysurjya | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:02 | Us:103 | 1 | POJO class for Course | Joysurjya | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:03 | Us:104 | 1 | Create POJO class for Training Program | Sneha | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:04 | Us:110 | 1 | Create POJO class for Feedback | Arpan | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:05 | Us:101 | 1 | Create POJO class for Participant | Neha | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:06 | Us: 130 | 1 | Create POJO class for Trainer | Sneha | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:07 | Us:111 | 1 | Create POJO class for Login | Neha | 2021-07-22 12:00 | 2021-07-22 17:00 | Nil | Done
P:08 | Us:101 | 1 | Make Database and apply annotation and all required validation in POJO classe of Participants | Neha | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:09 | Us:103 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Courses | Joysurjya | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:10 | Us:104 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Training Program | Sneha | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:11 | Us: 110 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Feedback | Arpan | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:12 | Us: 130 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Trainer | Sneha | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:13 | Us:111 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Login | Neha | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:14 | Us:113 | 1 | Make Databse and apply annotation and all required validation in POJO classe of Admin | Joysurjya | 2021-07-23 11:00 | 2021-07-23 17:00 | 2021-0-25 5:00 PM | Done
P:15 | Us:101 | 1 | Repository (Trainer) | Sneha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Sneha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Sneha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
P:16 | Us:124 | 1 | Repository (Courses) | Joysurjya | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Joysurjya | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Joysurjya | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
P:17 | Us:122 | 1 | Repository (Training Program) | Pushpanjali | 2021-07-28 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Pushpanjali | 2021-07-28 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Pushpanjali | 2021-07-28 12:00 | 2021-07-29 18:00 | Nil | Done
P:18 | Us:111 | 1 | Repository ( Feedback) | Arpan | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Arpan | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Arpan | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
P:19 | Us:122 | 1 | Repository (Participant) | Neha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Neha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Neha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
P:20 | Us:111 | 1 | Repository (Admin) | Joysurjya | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Joysurjya | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Joysurjya | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
P:21 | Us:130 | 1 | Repository (Login) | Neha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 2 | Service Implementation | Neha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
|  | 3 | Controller methods | Neha | 2021-07-27 12:00 | 2021-07-29 18:00 | Nil | Done
P:22 | Us:130 | 1 | Validations | Sneha | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Sneha | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Sneha | 2021-07-30 | 2021-08-01 | Nil | Done
P:23 | Us:111 | 1 | Validations | Joysurjya | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Joysurjya | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Joysurjya | 2021-07-30 | 2021-08-01 | Nil | Done
P:24 | Us:101 | 1 | Validations | Pushpanjali | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Pushpanjali | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Pushpanjali | 2021-07-30 | 2021-08-01 | Nil | Done
P:25 | Us:104 | 1 | Validations | Arpan | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Arpan | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Arpan | 2021-07-30 | 2021-08-01 | Nil | Done
P:26 | Us:130 | 1 | Validations | Neha | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Neha | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Neha | 2021-07-30 | 2021-08-01 | Nil | Done
P:27 | Us:111 | 1 | Validations | Joysurjya | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Joysurjya | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Joysurjya | 2021-07-30 | 2021-08-01 | Nil | Done
P:28 | Us:111 | 1 | Validations | Neha | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 2 | Exception Handling | Neha | 2021-07-30 | 2021-08-01 | Nil | Done
|  | 3 | Http Status Code | Neha | 2021-07-30 | 2021-08-01 | Nil | Done
P:29 | Us:130 | 1 | JUnit Testing using Mockito | Sneha | 2021-08-02 | 2021-08-04 |  | Done
P:30 | Us:111 | 1 | JUnit Testing using Mockito | Joysurjya | 2021-08-02 | 2021-08-04 |  | Done
P:31 | Us:101 | 1 | JUnit Testing using Mockito | Arpan | 2021-08-02 | 2021-08-04 |  | Done
P:32 | Us:104 | 1 | JUnit Testing using Mockito | Neha | 2021-08-02 | 2021-08-04 |  | Done
P:33 | Us:103 | 1 | JUnit Testing using Mockito | Pushpanjali | 2021-08-02 | 2021-08-04 |  | Done